## Waqar Tanveer
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Task 4 | Task 4 Progress | Task 4 Points | Super Task | Super Task Progress Report | Super Task Points
15-5-18 | Work on Hamed thesis before Break + Go to Open House and bring gifts. You will go from 10 to 11 | Arrived at 10 am because of official bank work as told yesterday. Attend open house from 10am to 1pm because in strat went to CS open house, there we spend almost 30 to 40 min then we move on to EE open house. In EE open house they first took us to conference room and we have to sit there amost 40 to 50 min because they are giving general ideas about open house to representatives of different companies after that they gave some to fill also they ask different questions about things in which company is dealing. After that they assign us an usher which took us to all EE labs and we checked different projects in almost 40 min. After that we went to HBL for clearing Ali's check. First we inform him to send the picture of crossed check so that we will deposit the cash to his account then Rizwan dont have a CNIC copy and also the office boy of HBL who normally do that type of work is also not present there so all of that bank procedure cost almost 30 to 40 min. After that we went back so there is no time left for Hameed project. | . |  | Project plan ready and I have shown you. I also sent you in email. | 3 | Work started according to plan | . | 2
16-5-18 | Work on Hamed thesis before break | Worked 3hrs wrote on topics related to Power Quality and factors which effect it. | 2 | Prepare project planfor pcb design of teslar project. You will make pcb for gsm for GRID and for SOLAR PANEL. | .Project plan finalized with collaboration of Hammad and uploaded (30Min) | 4 | Work on pcb design and follow plan which you will have prepared after showing me. | GSM PCB is almost finished (3 Hrs) | 4 | Meeting at Office | Had a Meeting at Office (30Min) | 1
17-5-18 | Do work as per project plan. Dont forget to update status on project plan sheet. If anything is in progress write 'In Progress ' and if anything is complete mention 'Completed' | GSM PCB Design completed and Wifi PCB Design is in Progress (6 Hrs) | 3
18-5-18 | Update project plan (30 minutes at max) | .Complete Project Plan uploaded which included both Prototype as well as Product module (1 Hr). 1 Hr consumed because of ammendment of multiple new things. | 3 | Do work as per project plan. Dont forget to update status on project plan sheet. If anything is in progress write 'In Progress ' and if anything is complete mention 'Completed'. Also mention time of completion for that task in project plan. | . PCB design of wifi is completed (3.5 Hrs) | 4 | Components List of Prototype | 2
19-5-18 | 0
20-5-18 | 0
21-5-18 | Tour to college road | Purchasing of components is completed (4 Hrs) | 5 | Visit to RND Lab | We visited the lab and discussed our PCB design (1 Hr) | 2
22-5-18 | Work on project as per project plan | Went to RND lab and met Sir Shahbaz. Worked on optimization of PCB Design. (4 Hrs) |  | Meeting with Sir Majid | Waited 2 Hrs but he didnt come (2 Hrs)
23-5-18 | Optimization in PCB Design | Optimization of PCB design is in progress. Arduino sensors which are not present in proteus are created manually and that step is completed. (3.5 Hrs) |  | Meeting with Chile Client |  | Meeting took place for almost 2 hrs in which I corrected some problems specially the connections between arduino and gsm (2 Hrs)
24-5-18 | Work on project as per project plan | Optimization of PCB design is in progress.(3 Hrs) | 2 | Meeting with Chile Client | Resolve the issues of AT commands but he is not receiving data because of No balance in the sim (3 Hrs) | 2
25-5-18 | Hameed project | Wrote 4 pages of thesis (3.5 Hrs) | 3 | Meeting with Chile Client | Sent him the latest running code but he didn't receive data (1.5 Hrs) | 2
26-5-18
27-5-18 | 0
28-5-18 | Work on Hamed thesis | Wrote 6 pages of thesis (6 Hrs)
29-5-18 | Work on Hamed Project | Wrote 2 pages (2.5 Hrs) |  | Meeting with teslar client to resolve gsm issue | Meeting took 3 Hrs but still get no solution of his problem. May be we are facing network problem. (3 Hrs) |  | Github meeting, Account creation, Git Bash installation | Completed (30 min)
30-5-18 | 0
31-5-18 | 0
0

## Umair
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Super Task | Super Task Progress Report | Super Task Points
15-5-18 | Work on Major Babar Project | 1) Literature review already in introduction, currently explaining it2) Proof reading. | 3 | Send grid data (current+voltage) to serverusing GSM | Done with some help from Hammad | 4 | Go to Open Houseand bring gifts. You will go from 10 to 11 | Didnot go there as i arrived late in office due to issue with my salary cheque and did task 2 instead. | 0
16-5-18 | Work on Major Babar Project before Break | 1) I have added some flow chart of algorithms2) Some new references are added and now paper needs to formatted | 4 | Make project plan for home automation | made the plan please review it | -2(Please check 'Status' and 'Prerequisite' columns of your project plan). Can consult with hammad and waqar.
17-5-18 | Updata project plan (30 minutes at max). | Got the working link at 10:40 am, updated the plan in about 30 mins | 3 | Do work as per project plan. Dont forget to update status on project plan sheet. If anything is in progress write 'In Progress ' and if anything is complete mention 'Completed' | Prepared the project feasibility report in 4 hours, before 10 am I got its prereq information from hammad after that I prepared it and emailed to Mr. Sajid | 3 |  | Task 3: Worked 1 hour on major paper emailed revised draft to Mr. Sajid | 2
18-5-18 | Do work as per project plan. Dont forget to update status on project plan sheet. If anything is in progress write 'In Progress ' and if anything is complete mention 'Completed'. Also mention time of completion for that task in project plan. | Project plan updated as the project is discussed today and modified a bit | 3 | Update feasibility report after discussion | Feasibility report is updated emailed to Mr. Sajid | 3
19-5-18 | 0
20-5-18 | 0
21-5-18 |  | Task 1: help in major baber project from 10-12:30 pm, first i searched for computational time paper but could not find. then added some data in excel file. | 2 | Task 2: worked on wifi module, configured my laptop's arduino IDE for WeMos D1 for 8 to 10 am. |  | 3 |  | Task 3: went to R&D lab with hammad and waqar from 12:30 pm to 2 pm. and asked them about their service | 2
22-5-18 | 0 | Task: Arduino Code for home automation, worked on wifi module learned about its code and how to interface SD card with arduino further tests tomorrow with SD card, from 8 to 11 am |  |  | Went to R&D lab from 11 am to 1:30 pm, meeting with Mr. Shahbaz where he raised the point on further optimizing the PCB layout and reducing its size moreover he showed how to make new parts libraries in Proteous
23-5-18 | Work as per project plan | Worked on interfacing the SD card module with Arduino Uno. The card module is interfacing with arduino, tomorrow testing and storing data in SD card through arduino (2 hours) |  |  | Made a project plan desciption word file after an extensive meeting Mr. Sajid. In this file the project plan made in excel is described. (1100-1300) (3 hours) |  |  | Worked on Omer kanan project (1 hour)
24-5-18 | Work on Omar kanan project. Have meeting with him at 12 today | changed to PID controller to NN controller in HARP, implemented H-bridge inverter. Meeting with Mr. Omer, he says to implement modular inverter (8-1330) (5:30 hours) | 3 |  | interfaced SD with ardino, ardiuno is storing data on sd card now I will work on how to fetch data from sd card through arduino (30 mins) | 3
25-5-18 | 0
26-5-18 | 0
27-5-18 | 0
28-5-18 | Complete omar kanan work | Implemented Modular inverter, 7 levels. without filter it shows THD of 19%, with first order filter it shows THD of 18% and with second order filter it shows THD of 3%. Now i will work on adding active power filters to it. (6 hours)
29-5-18 | Work on Omar kanan project. Have meeting with him at 12 today | implemented hybrid filter to yesterday implemented modular inverter, it shows good results however further improvements can be made, skype conversation with Mr. Omer he says to implement latest gate control strategy. (5:45 hours) |  |  | Github account creation and sending username to Mr. Sajid (15 mins)
30-5-18 | Work on Omar Kanan Project
31-5-18 | 0

## Sameer Tasks
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Super Task | Super Task Progress Report | Super Task Points | Task4 | Task 4 Progress Report | Task 4 Points | .
15-5-18 | Prepapre code for only scrapping categories having less than 30 products. Later we will change this 30 to 50 | completed and running on server | 5 | Run data analyticsbut only after completion of task 1 | In progress, having issue with resetting whole code and removing ambigious code | 3 | 1-Prepare API for Kahif Website. Discuss with Asad about API.2- Give 1400 IPs to Kahisf and note down number of scrapped products the next day. Dont forget to note time and number of products before giving 1400 ips. | code structure is change in ebay, we will need more IPs in amazon, beacuse amazon detect ips quickly than ebay, and disscuss about api with asad. | 1 |  |  |  | had meeting with chillie client, i took almost 20 minutes | 3
16-5-18 | 1-Check scrapping status of products of bob and use all 1400 IPs for bob scrapping. 2- Use Kashif 100 IPs for his scrapping and note down the status | products:22248, reviews:569881 | 2 | [6 empty] | Complete data analytics and scoring of bob project. After today data should be automatically displayed on website | done took 4 hours setting and testing code and upload it on server | 50 | had meeting with sir sajid, kashif and asad bhai discussing projects of kashif , it took 3 hours collectivly |  | 3
17-5-18 | 1- Check status of bob data analytics 2- Check status of kashif scrapped products with 12 ips at 5 pm today. | -perform analytics on products:3662 -perform analytics on reviews:144399 and run amazon handbags category on 12 ips it gets 239 products in last two hours | 3 | Work on scheduler for Kashif scrapping. | work in progress, code has been written just have to test it and have to discuss some issues | 2 | Finalize databases for kashif work if get time. | 0
18-5-18 | Finalize scheduler for Kahisf | almost done, giving system error while adding cron parameters, will resolve it shortly | 1 | Make APIs for Kashif | -5 |  | Check status of bob products and analytics | analyzed products:8057, analyzed reviews: 251625, product_with_rank_zero:8266 | 1 |  |  |  | make report for operating iot_Server | done and send it on skype and on your mail | 5
19-5-18 | 0
20-5-18 | 0
21-5-18 | Complete and test scheduler | move forward, from earlier error which i told you , but beacuse od api i started late and after that electricity went off | 0 | Check data analytics status of bob and scrapping status of Kashif | analyzed products:19831 , analyzed reviews:500446 , product_with_rank_zero:2405 and scrap handbag category:1537 | 5 | Resolve scrapping issue of kashif | analyze the issue, it is beacuse of kashif's ip, i tested it with bob's ips and it work fine | 5 |  |  |  | Work on APIs if needed by Asad and Abid. | done from my side, i gave them data by uploading code on server. and here is ip 138.197.203.172:9000/docs | 3
22-5-18 | Send me server details of dispenser project with key | done, send you at "sajid@eveati.com" | 2 | Deploy Kashif code on bob server | done deploy on amazon. | 3 | Update urls for front end of bob website. | done, guide rizwan and inform asad bhai about categories | 3 |  |  |  | complete scheduling and give write python script to give category column to shoes | done | 3
23-5-18 | Check product analytics status of bob products. Start scrapping for categories having less than 20 products. Also note down total number products and reviews before scrapping. Also note start time of scrapping. | analytic is complete, no_of_products=22100, time_of_starting_scraper=11:00 |  | meeting on skype with chillie client | it took almost one and half hour |  | adding category in shoes product | it took 3 hours |  |  |  |  | meeting with kashif on phone, | call duration was 20 minutes, i ask to him to buy 500 ips because he is complaing about he is not getting data, he will come tommorow. after that i try to run scraper locally but data was not coming complete because of ips. | 2
24-5-18 | Work on Kashif project. Why his code is not working on server ? | got 500 ips and put it on server, ran amazon_handbags url on 2:30pm with 250 ips and got 2331 products and scraper is still running, and got run ebay locally and got 980 prodcuts | 4 | study aws private and public subnet and RDS service of aws | 2
25-5-18 | 0
26-5-18 | 0
27-5-18 | 0
28-5-18 | Check status of bob products and kashif products | bobs ips are finished and analytics is also performed, kashif's beauty category is remaining, i called hin infront of you, but he didn't call me back |  | Compete database etc for kashiif website. Also complete change of description through python code. I will send you code which Maqsood did. | can't do this now untill abid test it, which columns he would get easily and show it on site |  | Write code for automatically starting scrapping in case it stops. Make a check to see if scrapped products of a specific category are less than 90% of total products, re run the scrapper for that category. | started for kashif but, as i merging code of amazon shoes they had changed the whole layout of page, they hide data inside the javascript which is not easy to retrieve , but i am on it. |  |  |  |  | check seleniium on other sever | still problem is same
29-5-18 | 0
30-5-18 | 0
31-5-18 | 0

## Hafsa Asad Tasks
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Super Task | Super Task Progress Report | Super Task Points
15-5-18 | Run major babar code for real results | code is still running. will complete by tomorrow | 2 | Work on mimo Yasir paper before break | tried to understand the paper, but lots of things are still not clear. found a code online that gives same x/y axis graph as paper but that uses a different beamforming technique. i am trying to understand this code to edit it accordingly | 2 | Work on Mimo shah jehan paper after break. | studied and understood basic concepts like mm wave, massive mimo, RF, beamforming. started understanding and editing a matlab code of beamforming in mimo that i found from net vvb | 2
16-5-18 | Check and update status of major babar code | 97 instances have run. i had modified code so as not to get any inaccurate solutuon (that doesnt meet constraints). now we are not getting any better result, not even one | 2 | Work on mimo Yasir paper before break | studied the paper again but could not understand how to start implementing | 0 | Work on Mimo shah jehan paper after break. | .understood the paper furter. code for massive mimo transmission is done. i searched for relevnt codes on the net. most useful code is of paper https://arxiv.org/pdf/1601.07340.pdf(2016)that i found at https://github.com/yuxianghao/Alternating-minimization-algorithms-for-hybrid-precoding-in-millimeter-wave-MIMO-systems. it has the same channel and precoder/ combiner metod as our paper | 4
17-5-18 | Make proposal for Bero | done | 5 | Make another proposal for Bero |  | 5 | done
18-5-18 | 0 | [8 empty] | Complete major Babar paper | its complete, only the tables need to be inserted to the word document from excel sheet of result | 50
19-5-18 | 0
20-5-18 | 0
21-5-18 | Send proposal to freelancer for research papers (1Hour). Dont write formal proposal just tell him about projects on which we can write research papers. | i have sent him 5 ideas | 5 | Check project of freelancer that is related to regression/classification and decide budget and time. 2 Hours | it is a collection of 6 projects. 5 small projects and 1 large. the 5 small projects should take 12 days and the big project will take 2-3 weeks. it includes all project reports. i have sent you email with details | 5 | Work on Mimo shah jehan paper. | .took help from net toolbox to incorporate saleh valenzuel channel and analog precoder and analog combiner to our main code. now working on adding RF chains at sender and receiver ends | 3
22-5-18 | 0
23-5-18
24-5-18 | Work on Mimo paper
25-5-18 | Work on Watermarking project |  |  | Make proposals for shireen
26-5-18 | 0
27-5-18 | 0
28-5-18 | Write proposal |  |  | Work on bat algorithm for mimo
29-5-18 | 0
30-5-18 | 0
31-5-18 | 0

## Asad Mehmood Tasks
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Super Task | Super Task Progress Report | Super Task Points
15-5-18 | Work on Integration of Kahif website with APIs from sameer. | Kashif provided hosting details and I have installed wordpress there, but Nameservers were not applied for his domain, I informed him to contact their support or provide me nameservers | 1 | Work on BOB mini website after break. | I have made modifications on bob mini site, added arrows and home icon in menu, changed images and banners on all pages, created terms and privacy policy. | 4 | Discuss Project Plan for solar panel with Abid | Discussed project plan with abid and skipped extra layout work which required 12 hours because it was not compulsary, also reduced time from 12 hours to 4 hours for consumer homepage creation as we can reuse some code from user details page for manager. | 5
16-5-18 | Integrate kashif theme with hosting server | His hosting issues are not fixed yet, So I have installed wordpress on our domain "zimadar.com", also integrated his premium theme, it is ready to start work now | 3 | Complete work given by bob till now for his mini website | completed modifications for bob site, updated footer, updated buy now page and added buy now section with details, changes contact us image on all pages, updated homepage | 3 | Meeting with Kashif | had meeting with kashif and discussed about his server and hosting issues, asked their support to fix it, also discussed about appearance of his website to start work | 3
17-5-18 | Work with Abid in getting data from sameer to wordpress website in different categories as discussed. You can do testing with bob data and after complete testing sameer will prepare APIs for you. You can get data of Footwear, clothing etc from amazon just like as bob website. You will send category name and in response will get all products and sub categoriesbelonging to that category. If you are unable to get and display sub categories while passing main category name to rest api, dont spend much time (not more than 1 hour)and just send all categories (main and sub categories separately) and get products respectively. | I have integrated woocommerce to work with products, then we implemented a code to test product insertion in database using woocommerce api, now abid is trying to insert data from api, we have changed the way to insert data into database, because using older method, it requires to make more than 100 entries for a single product in multiple tables, it is much better way to perform this operation using woocommere api | 3 | bob mini site extra work | worked from home on bob mini site and completed popup with his email, it is now functional | 4
18-5-18 | Fetch products from sameer and display in your website in respective categories as discussed before. | Helped abid to save categories and images in database | 2 | Complete bob work mentioned in Version2 document | working on bob site version2, completed 3 out of 10 tasks/modifications | 4 (You did not send back document on skype group as discussed)
19-5-18 | bob site version II | completed 4-7 modifications of version II, details can be seen in doc shared in the group | 4
20-5-18 | bob site version II | completed 8-9 modifications of version II, details can be seen in doc shared in the group | 4
21-5-18 | bob site extra work | had conversation with bob and implemented extra changes including contact forms fields and styling the email for subscribers | 2 | [6 empty] | Display products in respective categories of kashif website through APIs. Layout/Design can be set later but need to display all products in different categories. Shoes will contain shoes products etc | we have saved products from multitested for testing. I have created categories and provided category ID's to abid and sameer to get products from api, images and categories are also getting into database now, abid is working on changes to be made for new api to store new products, products will be displayed when he saves into new product list | 0
22-5-18 | Complete yesterday supertask | our code is ready and tested on api for multitested, it worked well, api for mody.pk is not recieving data from api yet, we have informed hostgator support to open the port for required domain |  | Check categories issue on bob website. Send me complete status that how many done and how many left. | added available categories to multitested menu, working now |  | Work on bob website(not more than an hour) | fixed his homepage issues, also fixed issues related to ssl which blocked cookies
23-5-18 | Work on design of layout of Kashif website | abid was absent, you told me to work on bob site and I have completed all changes he demanded after version 2
24-5-18 | bob site | finished all modifications and extra work on bob site | 5 | Create back of all websites and mail me | created backups of multitested, Teslar and FucoidanPhoenix website files, also create backup of their databases | 4 |  |  |  | Work on kashif website | products are now fetched into wordpress database and displayed category by category on homepage, currently 3 categories are available, it will automatically display more when available | 25
25-5-18 | Bob Website |  | 3
26-5-18 | 0
27-5-18 | 0
28-5-18 | Work on Bob website | working on new homepage, shared link in group on skype |  | Work on Kashif website | fetched more products to database, available categories and products can be seen on homepage.
29-5-18 | Complete bob website
30-5-18 | 0
31-5-18 | 0

## Sajid Tasks
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Super Task | Super Task Progress Report | Super Task Points
15-5-18 | Watch and understand 10 to 48 videos of android development by Bucky | . | 1 | Meeting with Machine learning Trainers at 2:30 with talal | Done meeting with 2 trainers. It went well.Now need to finalize course contents and need to start marketing. We will organize seminars after Eid andwill start marketing in Ramzan. We will organize different training sessions for Python, Machine learning, advance machine learning, big data (spark, hadoop) and may be ethical hacking. | 4 | 1-Discussing progress and project plans with asad, abid, hammad, waqar, sameer2- Checking datasets of maqsood | . | -2
16-5-18 | watch and understand 25- 48 videos of android development by Bucky | . | -3 | Provide sample project plan to all | 2
17-5-18 | watch and understand 26- 48 videos of android development by Bucky | could not watch any video | -5
18-5-18 | watch and understand 25- 48 videos of android development by Bucky | watched all videos from 25 to 48. Took almost 7 hours. Fragment videos took more about 3 hours in troubleshooting and then I left them and moved forward. I will troubleshoot the problem if it occurs in project. Could not get enough time in office to complete videos so completed them on Saturday from home. | 5
19-5-18 | 0
20-5-18 | 0
21-5-18 | 0 | [8 empty] | 1- Make a separate application in which there will be list of available BT devices and there will be option to choose any of these devices. After connecting with psoc, send data as done in sample application. No extra code should be there in project. | Done. Spent around 7 hours on it. Have made application PSOCTesting_3. Have separated most of the extra code and files from code. Now we can integrate that code with our own application by understanding it. | 50
22-5-18 | Complete testing of login page with server. |  | Linking psoc application with login page of our application.
23-5-18 | 0
24-5-18 | 0 | [8 empty] | 1- Make application from scratch and test Login Activity with database/shared preferences. 2- Check and test sessions 3- Integrate psoc code after login activity Check and test code related to login activity on server (node js) | I editted something from gradle in c drive and then kept getting error related to gradle. I created many projects but continued getting same error. Finally I uninstalled and then reinstalled android studio. This whole process of trouble shooting and installing android studio, installing emulator took almost 4 hours. | -50
25-5-18 | 0
26-5-18 | 0
27-5-18 | 0
28-5-18 | Complete Login screen with forgot password, register new user with local database. |  |  | Run node js code on server and check the APIs for login, forgot password, Register User and also check the database.
29-5-18 | 0
30-5-18 | 0
31-5-18 | 0

## Maqsood Shah
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Super Task | Super Task Progress Report | Super Task Points | .
15-5-18 | Send me excel files of data generated by simulator | i have sent datasets xls files by email. | 4 | Fetch all publically available datasets having our desired parametersWrite and send a short report about dataset, inputs and outputs. | i have picked public available datasets for soil moisture and crop stage, wrote a report dataset details input,output parameters. | 4
16-5-18 | Finalize parameters for datasets. After today work only processing and applying algorithms should be left | i have finalized the inputs/outputs. sent you document email | 3 | Search for appropriate project plans. Maximum 1 hour. | created a project plan document. and handed over to Mr. Sajid | 5
17-5-18 | Finalize parameters for datasets. After today work only processing and applying algorithms should be left | yesrday i have finalized the inputs/outputs, but forgot to send email. just sent you email. | 1 | Apply NN if task 1 is completed or was completed yesterday. Also dont forget to mail me results. | writing code for regression analysis. | 1
18-5-18 | Complete and send me code | i have write some lines of code in python, i am facing difficulties to understand how to calculate the peak discharge, we have crop parameters, soil prameters, how to feed NN with these parameters to calculate peak discharge? i cant understand the dataset structure. | 2
19-5-18
20-5-18
21-5-18 | Apply NN on data and send me the code. | sent you an email. write code to predict values against orginal values. code is ok. dataset issues. dataset is not in propoer. for example: we need parameters like peak factor, storm duration, rainfall depth, initial abstraction ratio, basin area, curve number, time of concentration, these doen not exist in our data. |  | searching for valid datasets. 2 hours | could not found dataset that fulfill our needs. i have read others paper, could not get any help related to our scenario.
22-5-18 | literature review | read huma zia thesis and overview others paper |  |  | NN code review as written yesterday
23-5-18 | dataset preprocessing | crop stage and soil parameters have no direct relationship with peak discharge and time to peak so we need to preprocess our generated dataset. |  | meeting with marwan on phone (1 hour) | brief him about progress and discussion
24-5-18 | work on marwan project | email sent.normalized dataset.minimze input parameters.as we have to predict peak discharge. we have few inputs using in peak discharge.issue is we dnt have target values to predict. researhing(literature) how to predict target values if doent exist in case of NN. | 1(searching for NN without target values is not our goal. Please stick to the project)
25-5-18 | working on marwan project | email sent. review and modify code. makes some changes according to our dataset. stuck with dataset structure. we need a proper dataset with original peak discharge values, so we can apply algorithm to predict. | 1 | tensorflow tutorials (1 hour) | done:usage of examples, cheatsheet | -1(First complete the assigned work and then do extra things. We will do this work in Matlab, not python)
26-5-18 | 0
27-5-18 | 0
28-5-18 | [9 empty] | Make a complete requirements gathering document for this website https://www.cardmarket.com/en I am sending you login and password on skype. Messge me when you come online on skype and I will call you. | completed and sent by email.
29-5-18 | work on marwan project | writing code in matlab, but still confuse about dataset, it is not varified dataset. |  | Apply Tabu Search on any optimization problem and explain it. 1 hour at max | completed and sent report
30-5-18 | 0
31-5-18 | 0

## Rizwan Khan Tasks
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Super Task | Super Task Progress Report | Super Task Points
15-5-18
16-5-18 | 0
17-5-18 | Please check that whats the issue with formatting. Yesterday we changed colors and did other formatting to these files and in evening all was reset to default. | Slight changes were made for future correspondence. if these persists; than we move forward for further formattings. Along with this Late coming Minutes sheet was created and late coming points has been formulated. | 4 | PHP work as discussed before. | xamp was installed again as the previous was corrupt and database was created and trying to reconnect. | .
18-5-18 | Update points of all | Done | 4 | PHP work as discussed before. | keep working on that | 1 (Please write detail like how many videos you have watched )
19-5-18 | 0 | s
20-5-18 | 0
21-5-18 | Update points of all | Done |  | Work on Php lectures | 4 |  | Application for cheque book + Call for interview | Done | 4
22-5-18 | Update points of all | Done |  | Work on urls of bob project and send me complete status | urls of (Video Games, Toys and Games, Health and Household, Beauty and personal care, baby, sports and outdoors) completed. Categories of (toys and games, Sports and outdoors) completed. today work on health and household and complete it till (health & household - house suppllies - household cleaning). Remaining are video games, baby, beauty and personal care. | .
23-5-18 | 0
24-5-18 | Work on categories file of bob | In progress
25-5-18 | Work on categories file of bob |  | In progress | 3
26-5-18 | 0
27-5-18 | 0
28-5-18 | Work on categories file of bob | 3 completed
29-5-18 | 0
30-5-18 | 0
31-5-18 | 0

## Hammad Zafar Tasks
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Task 4 | Task 4 Progress | Task 4 Points | Super Task | Super Task Progress Report | Super Task Points
15-5-18 | Prepare project plan for pcb design of teslar project.You will make pcb for wifi for GRID and for SOLAR PANEL. | Prepared the Project Plan for PCB Design and have emailed you with subject PCB Design Project Plan | 3 | Finalize Document for both prototypesi-e. prototype with gsm and wifi | Emailed you with subject:Prototype Documentation(GSM&Wifi) | 5 | Start work on project plan | In progress | 1 | Have conversation with Client | Had a conversation with the client via Skype Call | 4
16-5-18 | Finalize project plan as per template (30 minutes at max) | Finalized and uplaoded (30 Min) | 4 | Meeting with teslar client and trouble shoot his code | Had a Skype Conversation(4 Hrs) | 4 | Do work as per project plan | GSM PCB almost Completed(2 Hrs) | 4 | Meeting with Sir Sajid | In a Meeting for about 30min -40 min | 1
17-5-18 | Do work as per project plan. Dont forget to update status on project plan sheet. If anything is in progress write 'In Progress ' and if anything is complete mention 'Completed' | GSM PCB Design completed & debugging is in Progress (4Hrs) | 4 | Keep checking messages of teslar client on skype group and communicate with him in case he comes online. He said that he got new sim. | Had a Skype Conversation(2 Hrs) | 3
18-5-18 | Do work as per project plan. Dont forget to update status on project plan sheet. If anything is in progress write 'In Progress ' and if anything is complete mention 'Completed'. Also mention time of completion for that task in project plan. | Debugging of PCB Design in progress(4Hrs) | 3 | Update the project plan | Updated the project plan with another module having SD Card (2Hrs) | 3
19-5-18 | 0
20-5-18 | 0
21-5-18 | Work as per project plan | Went to College Road to buy the required components to complete PCB Design(4 Hrs) | 4 | R&D Lab Visit | Visited R&D lab,discussed PCB Design and asked them about available equipments | 2
22-5-18 | Help me run PSOC Code | Ran the sample code and tested with the given Android App.() | . | Work on project as per project plan | Visited the R&D Lab and modified the design as per instruction of the instructor in Lab(4 Hrs) | .
23-5-18 | 0
24-5-18 | Work as per project plan | Optimization & Debugging of PCB Design in progress(6Hrs) | .
25-5-18 | Work as per project plan | PCB Design Optimization still in progress. It is almost complete.(2Hrs) | 3 | Graph for Billing | A simple graph of Power Graph was drawn and sent. Also searched about how billing is done and what are the parameters to generate an electricity bill.(2 Hrs) | 3 (Discuss with me today) | Talk to Client | There was some issue with the server so couldn't completely implement the Wifi code on his computer.(1Hrs) | 2
26-5-18 | 0
27-5-18 | 0
28-5-18 | Work as per project plan | Optimization of PCB Design completed (6 Hrs)
29-5-18 | Work as per project plan | Worked on SD Card Reader (4 Hrs) |  | Official Meeting | Attended meeting and installed github(1 Hr)
30-5-18 | 0
31-5-18 | 0

## Abid Hussain Tasks
Date | Task 1 | Task 1 Progress | Task 1 Points | Task 2 | Task 2 Progress Report | Task 2 Points | Task 3 | Task 3 Progress Report | Task 3 Points | Super Task | Super Task Progress Report | Super Task Points
14-5-18 | 1-Complete 2 graphs of bob website. | Completed 3 graphs of bob website: Review spikes,Review trend and multiple single day reviewers. | 3 | Prepare Project plan of Teslar Project | Project plan of Teslar is created as instructed.
15-5-18 | Complete Total Bill of All Users on Manager Dashboard (Maximum 4 hours) | Completed total bill of all users plus Fixed total power consumption graph now showing data in percentage. | 5 | Discuss and finalize project plan for teslar (60 mints at max) | Discuessd and will try my best to complete tasks before given time. | 0 | Help Asad in integrating and customizing wordpress database in Kashif website work | asad was not working on Kashif site, but I have tested api with wordpress database | 0
16-5-18 | 1: Multi Auth System for Consumer 1 hours 2: Database update entries 1 hours 3-Consumer dashboard,power,billing 5.3 hours 3:Project plan remaining time | 1. Created multi authentication system, now consumer and manager will be redirected to different dashboards. 2. Updated database entries more than 150 entries 3- Consumer dashboard is created | 4 | Complete project plan | I was working on other three tasks ,project plan task was not assigned . I couldn't understand if I make plan then I get -5 and if I don't make still I get -5 please discuss with me if you accept my project plan I will make project plan else you can make project plan and assign tasks daily ... | 0
17-5-18 | Work with Asad in getting data from sameer to wordpress website in different categories as discussed. You can do testing with bob data and after complete testing sameer will prepare APIs for you. You can get data of Footwear, clothing etc from amazon just like as bob website. You will send category name and in response will get all products and sub categoriesbelonging to that category. If you are unable to get and display sub categories while passing main category name to rest api, dont spend much time (not more than 1 hour)and just send all categories (main and sub categories separately) and get products respectively. | We can't directly interact with wordpress database as I observed that to add a product we have to update more than 50 columns and multiple rows in different tables. So today I wrote a new php code now successfully inserting data to WooCommerce products you can check here when click on category it will fatch and insert products to wordpress database woocommerce products. link to check: http://zimadar.com/index.php/aws-test. Still there are some work to do with wordpresss database . There are some issues in inserting category and imagelink because WP databse has image file but we have to insert image link not file similarly wordpress has category id but we have to add category name , so need some reserch on this. Time spen 6 hours | 3
18-5-18 | Fetch products from sameer and display in your website in respective categories as discussed before. |  | -5 | Upload work done on teslar till now and send me link in progress report (30 minutes at max) | Teslar project is uploaded http://expertsvision.site Manager login : abid pass: abid123 Consumer Account login: shah password: shah123 | 4
19-5-18 | 0
20-5-18 | 0
21-5-18 | 0 | [8 empty] | Display products in respective categories of kashif website through APIs. Layout/Design can be set later but need to display all products in different categories. Shoes will contain shoes products etc | All product details now is successfully fetching from AWS and adding in wordpress database including Image and category it will fetch data on click and will insert in each category respectively. There are some issues in storing database when fetch large amount of data. will fix tomorrow | 0
22-5-18 | 0 | [8 empty] | Complete yesterday supertask | API is fetching data from multitested and succesfully inserted product details, categories and images. But there are some issues from Kashif API from sameer side and Hostgator. From my side it is working I have tested it with MultiTested Bob API and it is working fine . | 0
23-5-18 | 0
24-5-18 | [9 empty] | Complete super task. Today is the last day for that task. After that you will get points. I did not give points earlier because of server issue. Now sameer has deployed server to other aws account and its working now. | Successfully fetched data from new server. Now product details, price, images are fetching and inserting in respective category in wordpress databse. Super Task is completed. Check here braceletecharm category: http://zimadar.com/index.php/product-category/accesories/braceletecharms/ | 25
25-5-18 | Working on Teslar site | Worked on Teslar site. On Manager dashboard , manager can creaste new user's account and can insert user data. Task is completed and uploaded on http://expertsvision.site/ | 4
26-5-18 | 0
27-5-18 | 0
28-5-18 | Work on teslar project as per project plan and upload the latest work | Worked on Teslar Project Create New User Consumer Account. Error handling and database dupilcation constraint fixed. Check here http://expertsvision.site/adduser . User name is : abid password: abid123. Now manager can create new consumer account but error will be shown if email is used same for different consumers. Email id must be nique.
29-5-18 | 0
30-5-18 | 0
31-5-18 | 0